## FAAS Work Plan
FAAS Work Plan
2020-2022
FAAS Priority # | Priority Description | Required (R), Optional (O) | Extent of Work | Priority Lead | Priority Team Members
1 | Complete SDP 1.3 - Financial Audit Guidance (GUID 2900) | R | Most of the technical work is completed but there is a potential for more based on FIPP and PSC decisions. | Canada | Sweden, USA, AFROSAI-E, UK, IDI, UAE, India, Kuwait | ED not approved by FIPP for exposure due to the need to further analyze the IFPP classification for this information. PAS raised concerns with respect to the current definitions of IFPP content in the drafting conventions and FAAS agreed that these are problematic therefore these definitions may be changing which could impact the classification. Next action: A workshop will take place at the PSC meeting to discuss the Due Process including the process to develop drafting conventions. Analyze the due process to propose revisions in June at the PSC meeting.
2 | Complete SDP 1.2 - Principles of Financial Auditing | R | Clearance of exposure comments | ECA | Kuwait | Presently open for comment with comments due by June 25th, 2019.
3 | Analysis of ISA 315 revisions to assess the impact on GUID 2900. Work with the Internal Controls Subcommittee to assess the potential impact of ISA 315 revisions on public sector internal control frameworks | R | Significant changes being proposed by IAASB. Development of a concept paper to be presented to the Internal Control Subcommittee. | Canada (part 1), USA (part 2) | UK, South Africa, Kuwait | Work not yet started. Next action: FAAS Secretariat will look at the status of ISA 315 revisions to determine FAAS timeline. Discuss the idea of creating a public sector internal control framework with the ICS (USA to lead).
4 | Analysis of ISA 600 revisions to assess the impact on GUID 2900. | R | Identify public sector considerations not presently addressed in GUID 2900. FAAS Secretariat to facilitate interaction with IAASB. | UK, South Africa | Norway, AFROSAI-E | Next action: FAAS Secretariat will look at the status of ISA 600 revisions to determine FAAS timeline.
5 | Analysis of ISQC 1 revisions and ISQC 2 to assess the impact on ISSAI 40. | R | FAAS resource to be part of PSC project. | PSC | Cameroon, ECA, Canada, Namibia, IDI, Sweden, UK, Ireland | ECA leading, FAAS comments due by May 20, 2019.
6 | Analysis of changes to ISA 220 to assess the impact on GUID 2900. | R | Identify public sector considerations not presently addressed in GUID 2900. | ECA | Cameroon, Canada, Namibia, IDI, Sweden, UK | ECA leading, FAAS comments due by May 20, 2019.
7 | FAAS technical support of IDI (financial audit icat and handbook, cooperative audits, and QA). | R | Technical reviews of developed financial audit information. IDI funded FAAS technical assessments of SAIs? | TBD once MOU is avaialble. | UAE, Canada, Cameroon, Sweden, AFROSAI-E (tentative commitment but depedent on MOU) | FAAS Secretariat will write first draft of the MOU and will send it to IDI and will circulate to FAAS members.
8 | FAAS technical support of AFROSAI-E financial audit manual. | R | Technical review of developed financial audit information. | UAE | UAE, Canada, Cameroon, Sweden, IDI | Contact AFROSAI-E to request the current version of the manuals (financial and compliance).
9 | FAAS community of practice on data analytics and UN Sustainable Development Goals (SDGs). | O | Development of website content | Norway | UK (analytics), UAE | Contact Norway to agree on a plan. FAAS Chair will work on linking to the internal control framework project above.
10 | Develop auditor reporting illustrative examples. | O | Continuing to work from examples already developed by IDI. | Canada | IDI | Contact Canada to agree on a plan.
11 | Analysis of developments in extended external reporting assurance. | O | FAAS resource to be part of PSC project. | PAS (FAAS Secretariat will coordinate) |  | Send an email to PAS FAAS to analyze
12 | Development of accounting research paper including consideration of developments in accounting for and auditing of smaller and less complex entities (differential reporting). Participation in round table discussions. | O | Multi-year project to develop: - ISSAI guidance - Advocacy guidance (maturity model) | UAE | IDI, AFROSAI-E, IAASB, IPSASB, South Africa, Austria (research paper) | FAAS Secretariat will develop a paper
Note on D11: Daniel Stephane Boutin: Dependent on MOU scope.
Note on D14: Daniel Stephane Boutin: Dependent on #1
Note on F16: Daniel Stephane Boutin: IPSASB will starting work on diff reporting in 2021, research now.