## Slide 1: Performance Auditing Subcommittee Work Plan 2011-2013
Summary of Proposed Actions and Progress Made
Presented by: Dagomar Henriques Lima June/2013
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 2: Proposed Action Create Forums and Media Presentations to promote and discuss PA documents
Progress Made
Creation of a community of practice for PAS members
Not Implemented
Discussion about ISSAI 3000 and 3100
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 3: Proposed Action Continue to develop the PAS website, including information and links to seminars and events, documents and examples of best practice reports.
Progress Made
Regular updating of the PAS webpage with information of last conferences and links to PA good practices guides
Not Implemented
Examples of best practice reports on the following audit themes: economy and efficiency, service delivery, effectiveness, performance information, performance management capacity, risk assessment and best practice review.
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 4: Proposed Action Translation of documents into other official INTOSAI languages (French, German, Spanish and Arabic).
Progress Made
ISSAI 3100 and its Appendix were translated into all Intosai official languages and into Portuguese.
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 5: Proposed Action Review/References of ISSAI 3000.
Not Implemented
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 6: Proposed Action Participation in the PSC Project for Harmonization of the ISSAIs and Revision of the Fundamental Auditing Principles.
Progress Made
PAS representatives in the Project: Tony Angleryd (2010 and 2011),Norbert Weinreichter and Glória Merola.
Development of ISSAI 300.
Participation in the development of ISSAI 100.
Exposure of the draft of ISSAI 300, inclusion of the comments made by SAIs and development of the endorsement version.
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 7: Proposed Action Participation in the activities proposed in the document PSC Awareness-raising Strategy.
Progress Made
Participation in the task force to disseminate the ISSAIs, which was dissolved when the 3i Programme was created.
Presentation made by the PAS Chair about the ISSAIs during the CReCER 2011 Conference.
Proposals of training events and other initiatives concerning ISSAIs presented by the PAS Chair within the Olacefs.
Participation of experts in performance auditing in the development of the iCAT (Dagomar Lima, firstly; Maria Lúcia Lima, in a second phase)
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 8: Actions not Included in the Work Plan
Progress Made
Development of the following guides (available on the PAS website):
Selecting performance audit topics;
Communication in the performance audit process;
Safeguarding quality in the performance audit process;
Making performance audit reports reader-friendly;
Designing performance audit: setting the audit questions and criteria.
Proposed Action
Development of guides on Performance Audit
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 9: Actions not Included in the Work Plan
Progress Made
5th PAS Meeting – Vienna, on February 27 to 29, 2012;
Participation in the International Seminar “Developing Institutional Capacities – experiences and challenges in performance auditing”, hosted by the State of Bahia Court of Accounts (Sharon, Jan, Inge);
Planning and coordination of 6th PAS Meeting – Ottawa, on May 27 and 28, 2013 .
Proposed Action Events organized and participation in events.
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 10: Terms of Reference for the PAS Main Proposals
Purpose
Promote the ISSAIs for PA
Mandate
  Harmonise the present collection of ISSAIs for performance auditing, and thereby ensure the consistency of the ISSAI Framework
  Promote the awareness of the ISSAI Framework and support the implementation of the ISSAIs for performance auditing in SAIs
  Continue to develop and maintain the ISSAIs and other guidance for performance auditing
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 11
Membership and PAS Chair
    Open and voluntary membership
    Size – between 10 to 20 active members
    PAS Chair is responsible for selecting members from volunteers, ensuring participation from SAIs representing different auditing systems, different languages and every regional working group
    PAS Chair is free to appoint observers
    PAS Chair should contact any member that didn´t attend a PAS meeting without explanation, to verify whether the SAI is still interested in being a PAS member
    It is suggested that PAS rotates the position of Chair after a maximum of 9 years
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 13: Project proposal Adaptation of the level 4 performance audit ISSAIs Presented by: Dagomar Henriques Lima June/2013
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 14: Summary
Scope and purpose
Background
Work programme, timetable and organisation
Resources and budget
Project management and governance
Transitional arrangements
Submission
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 15: Scope
“New” ISSAIs 100 and 300
ISSAI 3000 and 3100 and appendices
Five practice papers developed by PAS
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 16: Purpose
To lay down a set of PA standards on ISSAI level four
To adapt the present PA level four guidance in the light of:
  the adoption of the ISSAI 100 and 300 Fundamental Principles;
  the laying down of the set of PA standards under a) above.
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 17: Stages
The development of a set of auditing standards for performance auditing, based largely on the Fundamental Principles of Performance Auditing (“new” ISSAI 300) but also drawing if necessary upon the Fundamental Principles for Public Sector Auditing (“new” ISSAI 100).
The establishment of a new structure, numbering system and organization for guidance on the practical implementation of the new PA standards, including a proposal for how existing material, where relevant, might be organised under the new system.
Development of the guidance identified in stage 2, on the basis of existing material available in the “new” ISSAI 300 and the existing ISSAIs 3000 and 3100, including the appendices and the five practice papers.
Examination of the need for and development of supplementary PA guidance. This examination will include the relationship between PA guidance and the ISSAI 5000-series guidance.
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 18: Background
Auditing standards need to be explicitly set out at the fourth level.
In PA, there is no framework of internationally recognized standards.
PAS took the view that the existing guidance set out in the current ISSAIs 3000 and 3100 is rather comprehensive and needs to be reorganised and restructured on basis of the fundamental principles in the new ISSAI 300.
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 19: Work programme, timetable and organisation
Stage 1
Programme: Development of a set of auditing standards for PA, based largely on the “new” ISSAI 300 but also drawing if necessary upon the “new” ISSAI 100.
Activity | Timetable | Organisation
Analysis of “new” ISSAIs 100 and 300 to identify the standards necessary for PA to comply with the fundamental principles | 1st September 2013 | Working group of the SAIs of Canada (coordinator), Austria, Norway and UK
Drafting of a document (working title - “Standards for performance auditing”) which will eventually become ISSAI 3000 | 1st September 2013 | Working group of the SAIs of Canada (coordinator), Austria, Norway and UK
Circulation of document to all PAS members for comments | 1st October 2013 | All PAS members, coordinated by the SAI of Canada
Formal adoption by PAS of the document at its next meeting | Spring 2014 | All PAS members, coordinated by the SAI of Canada
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 20: Work programme, timetable and organisation
Stage 2
Programme: Establishment of a new structure, numbering system and organization for guidance on the practical implementation of the new PA standards, including a proposal for how existing material, where relevant, might be organised under the new system.
Timetable
1st October 2013 to 1st December 2013: preparation of a guidance concept by a working group
By 20th January 2014: approval of concept by PAS members
Organisation
Working group of SAIs of the Netherlands (coordinator), Denmark and Norway
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 21: Work programme, timetable and organisation
Stage 3
Programme: Development of the guidance identified in stage 2, on the basis of existing material available in the “new” ISSAI 3000 and the existing ISSAIs 3000 and 3100, including their appendices and the five practice papers previously developed by PAS.
The detailed programme, timetable and organisation of stages 3 and 4 will be decided at the next PAS meeting (Spring 2014) and will be the subject of an updated project proposal (along with a progress report) to be submitted to the 2014 Professional Standards Committee (PSC) meeting.
If progress is rapid and there is strong common agreement on stage 2, the PAS Chair may take the initiative to launch some stage 3 activities before the 2014 PAS and PSC meetings.
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 22: Work programme, timetable and organisation
Stage 4
Programme: Examination of the need for and development of supplementary PA guidance. This examination will include the relationship between PA guidance and the ISSAI 5000-series guidance.
Timetable and organisation
This exercise will be carried out during stage 3. If a need for further guidance to support the new ISSAI 3000 standards is identified, PAS will make a further submission to the PSC in due course.
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 23: Work programme, timetable and organisation
PAS estimations
New ISSAI 3000 will be ready for exposure by spring 2014
Set of guidance, based on the existing ISSAIs and practical documents will be ready for exposure by spring 2016
By then the assessment of need for further development of guidance will be finished and a proposal for work to be done will be submitted to PSC
PAS will re-examine its timetable at each annual PAS meeting
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 24: Resources and budget
Resources will be provided by participating SAIs
It will be for each participating individual SAI to assess and manage the resource implications of participation in this project
Language translation issues will be dealt with within this framework
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 25: Project management and governance
Chairmanship of PAS (SAI of Brazil)
The PAS chair will monitor progress through regular contacts with participating SAIs (and, particularly, with coordinating SAIs at each stage). It will further monitor and manage progress through its moderating of the PAS community “Moodle” site and through the annual PAS meetings
The PAS chair will report to the PSC as needed and at least annually
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 26: Transitional arrangements
Existing ISSAIs 3000 and 3100 (with the appendices) and the five practice papers should remain extant during the development process described above.
The formal exposure and adoption process could be handled in one of two ways:
  Immediate exposure and early adoption of the PA standards (the new ISSAI 3000) as quickly as possible after stage 1.
  This option would imply temporarily maintaining but renumbering the existing ISSAI 3000 so that the PA standards could take the designation “ISSAI 3000”. It would also imply adding a short note to the existing ISSAIs 3000 and 3100 to explain the transitional arrangements.
  Exposure and adoption only after completion of stage 3, with current ISSAIs 3000 and 3100 remaining extant (with their present numbering) until completion of this process.
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 27
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts
Both of the above scenarios should allow current SAI support work (such as that being carried out by the 3i programme) to continue in a stable environment. However, it will be important that the existing good communications between PAS and IDI continue and are even enhanced.
Option a) has the advantage of implementing the concept behind the revised ISSAI structure more quickly, whilst option b) has the advantage of one, rather than two, formal exposure, consultation and approval procedures.
To this end, the PAS Chair will copy the present document in its final (post PSC) form to IDI, invite IDI to join the PAS “Moodle” community and invite IDI to participate as an observer at future annual PAS meetings.

## Slide 28: Submission
PAS requests the PSC to:
  approve the present project proposal;
  advise PAS on any preference the PSC has on the adoption process (options a) and b) in point 6 above – Transitional arrangements).
INTOSAI – PSC
Professional Standards Committee
TCU
Federal Court of Accounts

## Slide 29
Thank you!