## FAS Projects
FAS Projects
Last Updated: |  | 2016-03-05
Key Dates
# | Project Status | Project Name (linked to Teamwork project folder) | Project Description | Project Leader | Project Team Members | Project Approved by PSC SC | Draft ISSAI Submitted to FAS Secretariat | Draft ISSAI Submitted to PSC SC for Exposure | End of Exposure Period | Final ISSAI Submitted to PSC SC for Publishing | Target Publishing Date | Notes
1 | ISSAI Draft Submitted to PSC SC For Exposure | Auditor Reporting - Subgroup 1 ISA 701 | Analysis of changes to auditor reporting ISAs to identify significant public sector considerations. | Sweden | New Zealand, ECA, Norway, UAE | 2014-05-19 | 2015-03-01 | 2015-05-28 | 2015-12-31 | 2016-03-30 | 2016-12-15 | FAS approved the PN presented at the 2016 FAS Annual Meeting subject to a few required revisions due to comments received from IAASB at the meeting. Revised PN received February 27, 2016. To be finalized for submission to PSC SC.
2 | Project Initiated and Ongoing | Auditor Reporting - Subgroup 2 ISA 260, 570, 700, 705, 706 |  | USA | New Zealand, Canada | 2014-05-19 | 2015-03-01 | N/A | N/A | 2016-03-30 | 2016-12-15 | FAS approved the PNs presented at the 2016 FAS Annual Meeting. To be finalized for submission to PSC SC.
3 | ISSAI Draft Submitted to PSC SC For Exposure | Auditor Reporting - Subgroup 3 ISA 210, 220, 230, 510, 540, 600, 710 |  | UAE | ECA | 2014-05-19 | 2015-03-01 | 2015-05-28 | 2015-12-31 | 2016-03-30 | 2016-12-15 | No exposure was required for these. Only ISSAI 1210 was revised. FAS Secretariat will submit revised ISSAI 1210 to PSC SC for their approval at their annual meeting in May 2016.
4 | Project Initiated and Ongoing | Auditor Reporting - Subgroup 4 ISA 800, 805, 810 |  | Norway (800,805), ECA (810) | UAE | 2014-05-19 | January 13th, 2016 (800,805) February 15, 2016 (810) | To be determined at 2016 FAS annual meeting if exposure is necessary. | To be determined at 2016 FAS annual meeting if exposure is necessary. | By March 30, 2016 if exposure is not necessary. | 2016-12-15 | 1800, 1805, 1810: Final revisions to be submitted to FAS Secretariat by 4th of March, 2016. To be circulated to FAS members until 18th March 2016 for their final clearance for submission to PSC SC for exposure. FAS Secretariat received 1800 and 1805 on March 1, 2016. Waiting for 1810.
5 | ISSAI Draft Submitted to PSC SC For Exposure | Internal Audit Involvement (ISA 610, 315, and conforming amendments) | Analysis of changes to internal audit ISAs to identify significant public sector considerations. | UAE | Sweden | 2013-06-17 | 2015-03-01 | 2015-05-28 | 2015-12-31 | 2016-03-30 | 2016-06-01 | UAE will revise based on comments received at FAS annual meeting 2016.
6 | ISSAI Draft Submitted to PSC SC For Exposure | Auditor's Responsibilities Related to Other Information ISA 720 and conforming amendments | Analysis of changes to auditor's responsibilities related to other information to identify significant public sector considerations. | USA | New Zealand, Canada | 2014-05-19 | 2015-03-01 | 2015-05-28 | 2015-12-31 | 2016-03-30 | 2016-12-15 | FAS approved the PN presented at the 2016 FAS Annual Meeting. To be finalized for submission to PSC SC.
7 | Project Initiated and Ongoing | Addressing Disclosures in the Audit of Financial Statements | Analysis of changes to audit of disclosures ISAs to identify significant public sector considerations. | UAE (South Africa) | Sweden, UK, USA | 2015-05-27 | Not yet received | To be determined at 2016 FAS annual meeting if exposure is necessary. | To be determined at 2016 FAS annual meeting if exposure is necessary. | By March 30, 2016 if exposure is not necessary. | 2016-12-15 | FAS did not identify a technical impact requiring a PN revision.
8 | Final ISSAI Submitted to PSC SC | Inclusion of ISAs in ISSAI by Reference | Separate ISAs from PNs and upload unmodified ISAs to ISSAI.org instead of trying to reproduce them. | UAE | Canada | 2015-05-27 | 2015-09-05 | N/A | N/A | 2016-05-01 | 2016-05-01 | The change has been made for the English version and is now published at ISSAI.org. FAS Secretariat is now working on all the other INTOSAI official languages. We are aiming to submit this information to PSC SC by the end of March 2016 to allow this to be completed before their annual meeting in May 2016.
9 | Project Initiated and Ongoing | Revision of ISSAI 200 and 1000 | Technical review and revision of ISSAI 200 and 1000 to eliminate redundancies and update them for ISA changes that have occurred. | ECA | Norway, UAE | 2015-05-27 | February 15, 2016 (ISSAI 200), February 18, 2016 (ISSAI 1000) | To be determined at 2016 FAS annual meeting if exposure is necessary. | To be determined at 2016 FAS annual meeting if exposure is necessary. | By March 30, 2016 for approval of exposure. | Not yet established | FAS concluded that ISSAI 1000 should be withdrawn and agreed with the proposed solutions for the text to be preserved and relocated with the exception of paragraph 47 which FAS decided to withdraw rather than relocate. FAS identified revisions required to ISSAI 200 and the project team completed the revisions and submitted a new version of revised ISSAI 200 to FAS Secretariat on March 2, 2016.
10 | Project Proposal Under Development | Roadmap for Sustainable ISSAI Implementation | Consultation exercise to identify possible solutions to facilitate the effective implementation of the ISSAI framework. Consultation will lead to initiation of one or more projects. | UAE | ECA, Sweden, (Brazil) | 2015-05-27 | Project proposal is presently under development | Project proposal is presently under development | Project proposal is presently under development | Project proposal is presently under development | Project proposal is presently under development | FAS has proposed the following two projects and they were discussed at the 2016 FAS annual meeting. 1) Roadmap for sustainable and effective ISSAI implementation: FAS concluded that PSC SC must own this project (since it's multidisciplinary) and must create a taskforce comprising members of FAS, PAS, CAS. FAS will propose option for possible deliverables. FAS believes that the first step will be to identify and organize information from SAIs that are presently on the journey to adopt the ISSAI framework (SAI Brazil) or that have complete this process recently (sources can include information from programs such as SAI PMF as well as other outreach activities of regions). The first sentence of the scope and timetable overview should be deleted. 2) Preconditions for effective financial audit ISSAI implementation: FAS decided that it's a FAS project to be initiated by FAS, needing an initial introduction explaining FAS' authority for undertake such a project. Under the task plan, the view was that the scope should be expanded to look at the requirements on Level 2. This must link to the Roadmap project. We have to clearly define the deliverable (guidance that links to an ISA requirement). The objective is to finalize the project proposals for submission to PSC SC for their approval at their annual meeting in May 2016.
11 | Project Initiated and Ongoing | Responding to Non-Compliance or Suspected Non-Compliance with Laws and Regulations | The ED includes those amendments that the IAASB has determined would be necessary to resolve actual or perceived inconsistencies of approach or to clarify and emphasize key aspects of the NOCLAR proposals in its International Standards. These amendments are based on the IESBA’s proposed NOCLAR amendments. | Norway | UAE, USA | Approval not required for PN revisions due to ISA revisions | Not yet received | Not yet submitted | Not yet determined | Not yet submitted | Not yet determined | The project team and FAS have not identified a specific public sector impact but are continuing to monitor the project as the IAASB activities are ongoing (IAASB is presently reviewing their own exposure comments and they will discuss these at their meeting in June 2016).
12 | Project Initiated and Ongoing | ITC - Enhancing Audit Quality in the Public Interest–A Focus on Quality Control, Group Audits and Professional Skepticism | The purpose of this consultation is to explore how the IAASB might best address, in the public interest, the calls for enhanced audit quality in the areas of quality control, group audits and professional skepticism. | Sweden (Professional Skepticism) | Canada (Quality Control), USA and UK (Group Audits) | Approval not required for submissions to IAASB | N/A | N/A | N/A | N/A | Target date to comment to IAASB is May 16, 2016 | The project team presented analysis done so far to FAS at the 2016 annual meeting and generated some comments. The project team will now continue their analyses, considering the feedback received at the meeting. FAS members should submit any additional comments to the project team by March 30, 2016. The project will finalize the proposed submission to IAASB by April 16, 2016 and this will be shared with FAS. FAS will provide their comments on the proposed submission to the project team by May 1, 2016. FAS will respond to IAASB on or before May 16, 2016.
13 | Project Proposal Under Development | Quality Review of All Practice Notes | FAS will perform a technical review of each Practice Note with the objective of ensuring technical integrity. | UAE | India, Norway, ECA, Sweden, AFROSAIE | Not required as this is part of the maintenance of the financial audit ISSAIs | [5 empty] | The result of the analysis will be summarized in one workbook and each paragraph that FAS decides should be retained will be classified by its nature to decide how it can be most effectively utilized (e.g: general guidance, application guidance, input to IAASB)
Other key points from the 2016 FAS annual meeting:
1) Formalizing interaction with IAASB (quarterly meetings, participation by IAASB on FAS' project team).
2) Potential future projects: Going Concern (Fiscal Sustainability)
3) Clearance from FAS members on merger with Accounting and Reporting Subcommittee. FAS members expressed some concern with the increased scope of work and size of the group but we ultimately concluded that this would be feasible and made logical sense. We will now communicate the approval to the Accounting and Reporting Subcommittee to allow them to clear the proposal with their membership.
4) FAS expressed concern with ISSAI 200 (duplication of requirements on Level 3 and Level 4). It is necessary because there is an option to audit in accordance with the ISSAI framework on Level 3 without Level 4 but because Level 3 repeats some of the requirements on Level 4, when Level 4 changes Level 3 must sometimes change also. This has the effect of destabilizing a principles document because it's too prescriptive. FAS has identified the duplication of technical content in ISSAI 200 as a significant technical problem and it will be raised with PSC SC.

## Timeline Calculator
Project Timelines
FAS Annual Meeting Date | 2016-02-24 | Allow 90 days between meetings to prepare submissions to PSC SC.
PSC SC Annual Meeting Date | 2016-05-26
| Exposure | No Exposure
Initiate Project Proposal Development (allow 60 days for development by FAS and processing by FAS Secretariat) | 2015-12-26 | 2015-12-26
Present Project Proposal at FAS Annual Meeting | 2016-02-24 | 2016-02-24
Present Project Proposal at PSC SC Annual Meeting for Approval | 2016-05-26 | 2016-05-26
Initiate Project (allow 120 days to develop and 150 days to develop and finalize for items not requiring exposure) | 2016-02-14 | 2016-06-18 | Note A
Submit Draft ISSAI to FAS Secretariat to Prepare Submission to PSC SC (30 days processing) | 2016-06-13 | N/A
Submit Draft ISSAI to PSC SC For Exposure (5 days processing by PSC SC once received) | 2016-07-13 | N/A
Start of Exposure Period (90 day exposure) | 2016-07-18 | N/A
Finalize Revision of ISSAI After Analysis of Exposure Comments and Submit Draft to FAS Secretariat (30 days to process comments received and finalize document) | 2016-10-16 | N/A
Submit Final ISSAI to PSC SC for Publishing (30 days for processing by PSC SC) | 2016-11-15 | 2016-11-15
Target ISSAI Publishing Date | 2016-12-15 | 2016-12-15
Note A
If this date is before the next PSC SC annual meeting date, a special approval is required to allow the project to be initiated before this meeting to meet the target publishing date.